SOFTWARE DEVELOPMENT

LIFE CYCLE

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TrueVoice

A Social Media Platform for Content Protection & Harassment Prevention

React.js  |  Node.js  |  Express.js  |  MySQL  |  Socket.io

| Field | Details |
| --- | --- |
| Document Type | Software Development Life Cycle (SDLC) |
| Project Name | TrueVoice — Social Media Platform |
| SDLC Model Used | Agile (Iterative & Incremental) |
| Version | 1.0 |
| Status | Active |
| Prepared By | Development Manager |
| Date | 18 March 2026 |
| Total Duration | 8 Weeks (2 months) |
| Total Phases | 6 Phases + Maintenance |

CONFIDENTIAL — INTERNAL DOCUMENT

# 1. Introduction

## 1.1 What is SDLC?

The Software Development Life Cycle (SDLC) is a structured process that defines every stage a software project goes through — from the initial idea to deployment and maintenance. It provides a disciplined framework that ensures the product is built correctly, on time, and meets all requirements.

For TrueVoice, we follow the Agile SDLC model — meaning we develop in short, focused iterations (sprints), with continuous testing and feedback at each stage rather than waiting until the very end to test. This allows us to catch problems early, adapt to changes, and deliver working software faster.

## 1.2 Why Agile for TrueVoice?

| Reason | How Agile Addresses It |
| --- | --- |
| TrueVoice has two novel features (Fingerprinting + Shield Mode) that need iterative refinement | Agile's sprint cycles allow us to test each feature independently before moving forward |
| Requirements may evolve as we learn more about the fingerprinting algorithm's behavior | Agile welcomes changing requirements, even late in development |
| College timeline is tight (8 weeks) | Agile delivers working software at the end of every sprint — always a demonstrable product |
| A small solo/duo development team | Agile removes heavy bureaucracy — lightweight process focused on working code |

## 1.3 Project Summary

| Attribute | Details |
| --- | --- |
| Project Name | TrueVoice |
| Core Problem Solved | Content theft (no credit for original creators) + Pile-on harassment (coordinated mass-commenting) |
| Unique Features | SHA-256 Content Fingerprinting (OriginPost) + Comment Velocity Shield (ShieldPost) |
| Tech Stack | React.js (Frontend), Node.js + Express.js (Backend), MySQL (Database), Socket.io (Real-time) |
| Target Users | Content creators and general social media users |
| Total SDLC Phases | 6 development phases + ongoing maintenance |
| Development Model | Agile — 2-week sprints |

# 2. SDLC Phases Overview

TrueVoice follows 6 core SDLC phases. Each phase has defined entry criteria, activities, deliverables, and exit criteria. No phase begins until the previous one's exit criteria are met.

| Phase 1 | Planning Define scope, timeline, resources, risks, and feasibility. Produce the project plan. |
| --- | --- |

| Phase 2 | Requirements Analysis Gather, document, and validate all functional and non-functional requirements. |
| --- | --- |

| Phase 3 | System Design Design architecture, database schema, API contracts, UI wireframes, and data flows. |
| --- | --- |

| Phase 4 | Implementation (Coding) Build the application phase by phase — backend first, then frontend, then integration. |
| --- | --- |

| Phase 5 | Testing & QA Unit test, integration test, and user acceptance test every feature before release. |
| --- | --- |

| Phase 6 | Deployment Deploy the application, finalize documentation, and submit for evaluation. |
| --- | --- |

| Phase ✦ | Maintenance Post-submission: bug fixes, performance improvements, future scope implementation. |
| --- | --- |

# Phase 1 — Planning

## Duration: Days 1–4  |  Sprint 0

Planning is the most critical phase. Poor planning is the single biggest reason software projects fail. In this phase we define WHAT we are building, WHY, HOW LONG it will take, WHO will do what, and WHAT COULD GO WRONG. Every decision made here directly shapes all later phases.

## 3.1 Objectives of Planning Phase

- Define the exact problem TrueVoice solves (content theft + pile-on harassment)

- Confirm the Agile SDLC model as appropriate for this project

- Break the project into phases and estimate realistic durations

- Identify all tools, technologies, and dependencies needed

- Perform feasibility analysis — is this buildable in 8 weeks by a college student?

- Identify risks and define mitigation strategies upfront

- Set up the development environment so coding can begin immediately after planning

## 3.2 Feasibility Analysis

| Feasibility Type | Assessment | Verdict |
| --- | --- | --- |
| Technical Feasibility | All technologies (React, Node, MySQL, Socket.io, SHA-256 hashing) are well-documented, free, and widely used. No exotic dependencies. | ✅ Feasible |
| Time Feasibility | 8 weeks for a full-stack app with 2 unique features is tight but achievable with daily progress and no scope creep. | ✅ Feasible (with discipline) |
| Economic Feasibility | All tools are open-source and free. Hosting can be done on free tiers (Render, Railway, PlanetScale). Zero budget required. | ✅ Feasible |
| Operational Feasibility | The platform is web-based, accessible via any browser, no special hardware needed for end users. | ✅ Feasible |
| Legal Feasibility | No third-party APIs that require paid licenses. No copyrighted content involved. GDPR not applicable for college scope. | ✅ Feasible |

## 3.3 Technology Stack Decision

| Layer | Chosen Technology | Alternatives Considered | Why Chosen |
| --- | --- | --- | --- |
| Frontend | React.js | Vue.js, Angular, Vanilla JS | Largest ecosystem, component model ideal for social feed UI, team familiarity |
| Backend | Node.js + Express.js | Django, Laravel, Spring Boot | Same language as frontend (JS), fast to set up, excellent for REST APIs |
| Database | MySQL 8.0 | PostgreSQL, MongoDB | Relational data model perfect for social graph, strong ACID compliance, college familiarity |
| Real-time | Socket.io | Firebase, Server-Sent Events | Bidirectional events needed for notifications + shield alerts |
| Auth | JWT | Sessions, OAuth only | Stateless, no session storage needed, refresh token pattern adds security |
| File Storage | Multer + Local | Cloudinary, AWS S3 | Multer is zero-cost for college scope; Cloudinary easy to swap in later |
| Hashing | Node.js crypto (SHA-256) | MD5, bcrypt for content | Built into Node.js — no package needed; SHA-256 is cryptographically strong |
| Email | Nodemailer | SendGrid, Mailgun | Free, zero setup, works with Gmail SMTP for college project |
| Scheduling | node-cron | Bull queue, Agenda | Lightweight — only one recurring job (shield checker) needed |

## 3.4 Risk Register

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-01 | Fingerprinting produces too many false positives (flags unique posts as duplicates) | Medium | High | Test with 100+ sample posts; tune normalization logic before Phase 4 |
| R-02 | Shield Mode triggers too aggressively on popular posts with legitimate engagement | Medium | High | Start with conservative threshold (15 comments/5 min); make it configurable |
| R-03 | MySQL query performance degrades on large datasets | Low | Medium | Add indexes from Day 1; test with 10,000 seed records before submission |
| R-04 | Socket.io connection drops causing missed notifications | Low | Medium | Implement reconnection logic on client; notifications also stored in DB as fallback |
| R-05 | File upload size causes server memory issues | Low | Medium | Set Multer limits (10MB images, 100MB video); reject at middleware level |
| R-06 | JWT token expiry causes poor UX (sudden logouts) | Medium | Medium | Implement silent refresh — auto-refresh access token using refresh token before expiry |
| R-07 | Running out of time for UI polish | High | Low | Backend-first approach; UI polish is Phase 7 — core features are always working first |
| R-08 | bcrypt password hashing too slow on weak dev machine | Low | Low | Cost factor 12 is standard; reduce to 10 in development environment |

## 3.5 Project Timeline (Master Schedule)

| Week | Dates | Phase | Key Deliverables |
| --- | --- | --- | --- |
| Week 1 | Days 1–7 | Planning + Requirements | Project plan, risk register, full requirements document, wireframes |
| Week 2 | Days 8–14 | System Design | DB schema, API contracts, component diagram, SDD complete |
| Week 3 | Days 15–21 | Implementation — Auth + Users | Register, login, JWT, email verify, profiles, follow system |
| Week 4 | Days 22–28 | Implementation — Posts + Fingerprinting | Post CRUD, media upload, SHA-256 fingerprinting, origin chain |
| Week 5 | Days 29–35 | Implementation — Feed + Interactions | News feed, likes, comments, language filter |
| Week 6 | Days 36–42 | Implementation — Shield Mode + Notifications | Cron job, shield activation, Socket.io notifications |
| Week 7 | Days 43–49 | Testing + Bug Fixes | Unit tests, integration tests, Postman collection, bug fixes |
| Week 8 | Days 50–56 | Deployment + Documentation | Live deployment, all docs finalized, submission ready |

## 3.6 Planning Phase Deliverables

| Deliverable | Status |
| --- | --- |
| Project Plan (this section) | ✅ Complete |
| Technology stack decision | ✅ Complete |
| Feasibility analysis | ✅ Complete |
| Risk register | ✅ Complete |
| Master project timeline | ✅ Complete |
| Development environment setup | ⬜ To Do (end of Day 4) |
| Git repository initialized | ⬜ To Do |
| MySQL database created | ⬜ To Do |

# Phase 2 — Requirements Analysis

## Duration: Days 3–7  |  Sprint 0 (overlaps with Planning)

Requirements Analysis is where we define EXACTLY what the system must do, broken into functional requirements (features) and non-functional requirements (performance, security, constraints). Every feature in Phase 4 (coding) must trace back to a requirement defined here.

## 4.1 Stakeholder Identification

| Stakeholder | Role | Key Interests |
| --- | --- | --- |
| College Examiner / Professor | Primary evaluator | Completeness, uniqueness, technical depth, documentation quality |
| End Users (Content Creators) | Primary users | Content credit, protection from harassment, clean notifications |
| End Users (General Users) | Secondary users | Easy-to-use feed, profiles, follow system, fast performance |
| Developer (You) | Builder & maintainer | Buildable in 8 weeks, learnable tech, impressive outcome |

## 4.2 Requirements Gathering Methods

- Competitive analysis — studying Twitter/X, Instagram, Reddit to identify gaps

- Research papers — reading published work on content attribution and online harassment

- Use case analysis — defining every user action as a use case with actor, precondition, and outcome

- Developer judgment — applying technical knowledge to define what is feasible within scope

## 4.3 Functional Requirements

### FR Group 1: Authentication

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-01 | User registers with username, email, password | Must Have | Low |
| FR-02 | Verification email sent on registration; account locked until verified | Must Have | Medium |
| FR-03 | User logs in with email + password, receives JWT access + refresh token | Must Have | Medium |
| FR-04 | Access token auto-refreshed silently before expiry | Must Have | Medium |
| FR-05 | User can log out (refresh token invalidated) | Must Have | Low |

### FR Group 2: User Profiles

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-06 | Each user has profile: avatar, bio, display name, post count, follower/following counts | Must Have | Low |
| FR-07 | User can edit their own profile | Must Have | Low |
| FR-08 | User can view any other user's public profile | Must Have | Low |
| FR-09 | User can follow or unfollow any other user (toggle) | Must Have | Low |

### FR Group 3: Posts

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-10 | User can create post with text and optional image or video | Must Have | Medium |
| FR-11 | Post is SHA-256 fingerprinted at creation before saving | Must Have (Unique) | High |
| FR-12 | User can edit their post text | Must Have | Low |
| FR-13 | User can delete their post (only their own) | Must Have | Low |
| FR-14 | Re-uploaded content auto-linked to original with credit badge | Must Have (Unique) | High |
| FR-15 | Each post shows an Origin Chain of all reshares | Should Have | Medium |

### FR Group 4: Feed & Discovery

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-16 | News feed shows posts from followed users, newest first | Must Have | Medium |
| FR-17 | Feed uses cursor-based pagination (no duplicate posts on scroll) | Must Have | Medium |
| FR-18 | Discover feed shows trending posts from non-followed users | Should Have | Medium |

### FR Group 5: Likes & Comments

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-19 | User can like or unlike any post | Must Have | Low |
| FR-20 | User can comment on any post | Must Have | Low |
| FR-21 | All comments pass language filter before going live | Must Have (Unique) | Medium |
| FR-22 | Non-follower comments queued (pending) when Shield Mode is active | Must Have (Unique) | High |
| FR-23 | Post owner can delete any comment on their post | Must Have | Low |
| FR-24 | Post owner can approve pending comments manually | Should Have | Low |

### FR Group 6: Shield Mode

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-25 | System monitors comment velocity per post every 60 seconds | Must Have (Unique) | High |
| FR-26 | Shield activates automatically at 15+ non-follower comments in 5 minutes | Must Have (Unique) | High |
| FR-27 | Shield auto-deactivates when velocity normalizes | Must Have (Unique) | Medium |
| FR-28 | Post owner can manually toggle Shield on/off per post | Must Have (Unique) | Low |
| FR-29 | Shield activation creates an audit log entry | Should Have | Low |

### FR Group 7: Notifications

| ID | Requirement | Priority | Complexity |
| --- | --- | --- | --- |
| FR-30 | Notifications for: like, comment, follow, shield activated, content reshared | Must Have | Medium |
| FR-31 | Notifications delivered in real-time via Socket.io (no page refresh) | Must Have | High |
| FR-32 | User can mark notifications as read (individual or all) | Must Have | Low |
| FR-33 | Notifications persist in database (not lost on reconnect) | Must Have | Low |

## 4.4 Non-Functional Requirements

| ID | Category | Requirement | Target Metric |
| --- | --- | --- | --- |
| NFR-01 | Performance | API response time for standard CRUD operations | < 300ms (95th percentile) |
| NFR-02 | Performance | News feed load time | < 500ms |
| NFR-03 | Performance | Real-time notification delivery latency | < 1 second |
| NFR-04 | Performance | Fingerprint duplicate check speed | < 50ms (indexed DB lookup) |
| NFR-05 | Security | Passwords stored as bcrypt hash | Cost factor = 12 |
| NFR-06 | Security | JWT access token expiry | 15 minutes |
| NFR-07 | Security | All protected routes validate JWT | 100% coverage |
| NFR-08 | Security | SQL injection prevention | Parameterized queries only |
| NFR-09 | Scalability | File upload size limit | Images: 10MB, Video: 100MB |
| NFR-10 | Usability | UI responsive across screen sizes | 360px to 2560px |
| NFR-11 | Usability | Browser compatibility | Chrome, Firefox, Edge (latest) |
| NFR-12 | Reliability | Shield cron job must not crash silently | Error logging + auto-restart |
| NFR-13 | Maintainability | Code organized into layers (controller → service → repository) | No direct DB calls in controllers |

## 4.5 Use Case Summary

| Use Case ID | Use Case Name | Primary Actor | Precondition |
| --- | --- | --- | --- |
| UC-01 | Register Account | Guest User | User has valid email, not already registered |
| UC-02 | Verify Email | Guest User | Registration completed, verification email received |
| UC-03 | Login | Registered User | Account exists and is verified |
| UC-04 | Create Post | Authenticated User | User is logged in |
| UC-05 | Detect Duplicate Content | System (Auto) | New post submitted with content matching existing fingerprint |
| UC-06 | Like a Post | Authenticated User | Post exists and user is logged in |
| UC-07 | Comment on Post (Normal) | Authenticated User | Post exists, Shield not active or user is a follower |
| UC-08 | Comment on Post (Shield Active) | Non-Follower | Post exists, Shield Mode is active on that post |
| UC-09 | Activate Shield (Auto) | System (Cron Job) | Comment velocity exceeds threshold |
| UC-10 | Activate Shield (Manual) | Post Owner | User is the owner of the post |
| UC-11 | Follow a User | Authenticated User | Target user exists and is not already followed |
| UC-12 | View News Feed | Authenticated User | User follows at least one person |
| UC-13 | Receive Real-Time Notification | System (Socket.io) | Triggering event (like, comment, follow, shield) occurs |
| UC-14 | View Origin Chain | Any User | Post exists and has reshare history |

# Phase 3 — System Design

## Duration: Days 8–14  |  Sprint 1

System Design translates requirements into technical blueprints. This phase produces the documents that developers follow during coding. Every architectural decision is made here — nothing important should be decided 'on the fly' during implementation.

📌 This phase produces the System Design Document (SDD) and Database Schema — both are separate detailed documents for TrueVoice. This SDLC section summarizes the key design decisions made in Phase 3.

## 5.1 Architecture Decisions Made in Phase 3

| Decision | Choice Made | Reason |
| --- | --- | --- |
| Architecture pattern | Layered monolith (Controller → Service → Repository) | Simpler than microservices, still cleanly separated for future extraction |
| Database type | Relational (MySQL) | Social graph data is naturally relational; strong JOIN performance for feed queries |
| Real-time strategy | Socket.io with user rooms | Each user joins a personal Socket.io room; notifications pushed server-to-client |
| Fingerprint algorithm | SHA-256 of normalized text + media file hash | Deterministic, fast, no external dependency, built into Node.js crypto module |
| Shield detection method | Cron job (60s interval) + comment status column | Background processing avoids adding latency to the comment API endpoint |
| Pagination strategy | Cursor-based (not page-number based) | Avoids duplicate posts when new content is added between page loads |
| Token strategy | Short-lived JWT + long-lived refresh token (hashed in DB) | Industry standard; refresh token hashed so DB breach doesn't expose valid tokens |
| File storage | Multer to local disk (Cloudinary-ready) | No cost for college; architecture supports Cloudinary swap without changing API |
| Error handling | Global Express error handler + asyncHandler wrapper | Single place to format all errors; prevents unhandled promise rejections |

## 5.2 Database Design Summary

| Table | Key Design Decision | Why It Matters |
| --- | --- | --- |
| users | verification_token cleared after use; refresh_token stored as hash | Security — plaintext tokens never persist after use |
| posts | is_reshare + original_post_id columns enable origin chain without separate table | Efficient — single JOIN to get reshare history |
| fingerprints | CHAR(64) + UNIQUE index on hash column | SHA-256 always 64 chars; UNIQUE index makes duplicate check O(1) |
| comments | status ENUM('approved','pending','rejected') — the engine of Shield Mode | One column controls Shield behavior; easy to query and audit |
| follows | Composite PRIMARY KEY (follower_id, following_id) | Prevents duplicate follows at DB level; fastest possible follow-check query |
| notifications | type ENUM includes 'shield_activated' and 'content_reshared' | Both unique TrueVoice events are first-class notification types |
| shield_events | Separate audit log table for shield activations | Never mix audit data with operational data; enables future analytics |

## 5.3 Phase 3 Deliverables

| Deliverable | Status |
| --- | --- |
| System Design Document (SDD) — full architecture | ✅ Complete (separate document) |
| Database schema — all tables, columns, constraints | ✅ Complete (in SDD) |
| API contracts — all endpoints documented | ✅ Complete (in SDD) |
| Component diagram — frontend components list | ✅ Complete (in SDD) |
| Service layer design — all backend services documented | ✅ Complete (in SDD) |
| Fingerprinting algorithm documented | ✅ Complete (in SDD) |
| Shield Mode cron logic documented | ✅ Complete (in SDD) |
| UI wireframes (low-fidelity) | ⬜ To Do |

# Phase 4 — Implementation (Coding)

## Duration: Days 15–42  |  Sprints 2–5

Implementation is where the actual code is written. We use an inside-out approach: database first, then backend API, then frontend UI, then integration. This ensures every layer is tested before the next one depends on it.

## 6.1 Coding Standards

- File naming: camelCase for JS files (userService.js), PascalCase for React components (UserProfile.jsx)

- Every async function wrapped in try-catch or asyncHandler — no unhandled rejections

- No business logic in route handlers — controllers call services, services call repositories

- No raw SQL strings concatenated with user input — always parameterized queries with mysql2

- Secrets in .env only — never hardcoded, never committed to Git

- Git commit after every completed feature — descriptive messages (e.g., 'feat: add SHA-256 fingerprinting on post creation')

- API tested in Postman after each endpoint is built — before moving to next

## 6.2 Sprint 2 — Auth System & User Profiles (Days 15–21)

| Task ID | Task | Estimated Hours | Dependencies |
| --- | --- | --- | --- |
| T-201 | Create MySQL database and run schema migrations for users table | 1h | Phase 3 schema complete |
| T-202 | Build UserRepository — all users table query functions | 2h | T-201 |
| T-203 | Build TokenService — JWT sign, verify, refresh token generation | 2h | T-201 |
| T-204 | Build EmailService — Nodemailer SMTP setup, send verification email | 2h | — |
| T-205 | Build AuthService — register, email verify, login, logout logic | 4h | T-202, T-203, T-204 |
| T-206 | Build auth routes + controller (POST /register, POST /login, etc.) | 2h | T-205 |
| T-207 | Build auth middleware — JWT verify, attach req.user | 1h | T-203 |
| T-208 | Build rate limiter middleware for login endpoint | 1h | — |
| T-209 | Test all auth endpoints in Postman (happy path + error cases) | 2h | T-206 |
| T-210 | Build follows table schema + FollowRepository | 1h | T-201 |
| T-211 | Build UserService — get profile, update profile, follow/unfollow | 3h | T-202, T-210 |
| T-212 | Build user routes + controller (GET /users/:id, POST /follow) | 2h | T-211 |
| T-213 | Build Multer middleware for avatar upload | 1h | — |
| T-214 | Test all user/follow endpoints in Postman | 1h | T-212 |
| T-215 | React: Build AuthContext, Login page, Register page | 4h | T-206 |
| T-216 | React: Build Profile page, Follow button, Avatar upload | 3h | T-212 |

## 6.3 Sprint 3 — Posts + Fingerprinting (Days 22–28)

| Task ID | Task | Estimated Hours | Dependencies |
| --- | --- | --- | --- |
| T-301 | Create posts + fingerprints tables schema | 1h | T-201 |
| T-302 | Build FingerprintService — SHA-256 generation, duplicate detection | 4h | T-301 |
| T-303 | Build MediaService — file validation (MIME + magic bytes), storage | 2h | T-213 |
| T-304 | Build PostRepository — CRUD queries including is_reshare joins | 3h | T-301 |
| T-305 | Build PostService — createPost orchestrating T-302 + T-303 | 4h | T-302, T-303, T-304 |
| T-306 | Build post routes + controller (POST, GET, PUT, DELETE /posts) | 3h | T-305 |
| T-307 | Build GET /posts/:id/origin-chain endpoint | 2h | T-304 |
| T-308 | Test fingerprinting: upload same image twice, verify credit badge | 2h | T-306 |
| T-309 | React: Build CreatePost page with drag-drop upload | 4h | T-306 |
| T-310 | React: Build PostCard component with OriginBadge | 3h | T-309 |
| T-311 | React: Build PostDetail page with OriginChain component | 2h | T-307 |

## 6.4 Sprint 4 — Feed + Interactions + Language Filter (Days 29–35)

| Task ID | Task | Estimated Hours | Dependencies |
| --- | --- | --- | --- |
| T-401 | Create likes + comments tables schema | 1h | T-301 |
| T-402 | Build FeedRepository — cursor-paginated feed query with JOINs | 4h | T-401 |
| T-403 | Build FeedService + feed route (GET /posts/feed) | 2h | T-402 |
| T-404 | Build LikeService + like repository + routes (POST /posts/:id/like) | 2h | T-401 |
| T-405 | Build LanguageFilterService — blocklist + regex scoring | 3h | — |
| T-406 | Build CommentRepository — insert with status, query by post | 2h | T-401, T-405 |
| T-407 | Build CommentService — create (filter + shield check), delete | 3h | T-405, T-406 |
| T-408 | Build comment routes + controller | 2h | T-407 |
| T-409 | Test language filter with toxic + normal comments | 2h | T-408 |
| T-410 | React: Build Feed page with infinite scroll / load more | 4h | T-403 |
| T-411 | React: Build CommentBox + CommentList components | 3h | T-408 |
| T-412 | React: Build Discover feed tab | 2h | T-403 |

## 6.5 Sprint 5 — Shield Mode + Notifications + Socket.io (Days 36–42)

| Task ID | Task | Estimated Hours | Dependencies |
| --- | --- | --- | --- |
| T-501 | Create notifications + shield_events tables schema | 1h | T-301 |
| T-502 | Build Socket.io server setup — user rooms, auth middleware | 3h | T-207 |
| T-503 | Build NotificationService — create record + emit Socket event | 3h | T-501, T-502 |
| T-504 | Build ShieldRepository — shield state, queue insert/release | 2h | T-401, T-501 |
| T-505 | Build ShieldService — velocity query, activate/deactivate logic | 4h | T-504 |
| T-506 | Build CronService — node-cron job calling ShieldService every 60s | 2h | T-505 |
| T-507 | Build shield routes (POST /activate, POST /deactivate, GET /status) | 2h | T-505 |
| T-508 | Integrate NotificationService into LikeService, CommentService, FollowService | 2h | T-503 |
| T-509 | Test Shield: simulate 20 rapid comments, verify auto-activation | 2h | T-506 |
| T-510 | Build notification routes (GET, PUT /read, PUT /read-all) | 2h | T-503 |
| T-511 | React: Build SocketContext + connect on login | 2h | T-502 |
| T-512 | React: Build Notifications dropdown + real-time bell counter | 3h | T-511 |
| T-513 | React: Build ShieldBanner on PostCard + manual toggle button | 2h | T-507 |
| T-514 | End-to-end test: full user journey from register to shield alert | 3h | All |

# Phase 5 — Testing & Quality Assurance

## Duration: Days 43–49  |  Sprint 6

Testing is not something we do 'at the end' — throughout Phases 4 we've been testing each API endpoint in Postman immediately after building it. Sprint 6 is dedicated to systematic testing across all layers, documenting results, and fixing all issues found.

## 7.1 Testing Strategy

| Test Type | Tool | What is Tested | Who Runs It |
| --- | --- | --- | --- |
| Unit Testing | Jest | Individual service functions — fingerprint hash generation, language filter scoring, token validation | Developer |
| Integration Testing | Supertest + Jest | API endpoints end-to-end — request in, database out, correct response | Developer |
| Manual API Testing | Postman | Every endpoint against its documented contract — happy path + all error cases | Developer |
| UI Testing (Manual) | Browser | All user flows on Chrome, Firefox, Edge at desktop + mobile viewport | Developer |
| Security Testing (Basic) | Manual | SQL injection attempts, expired token rejection, wrong-owner delete attempt | Developer |
| Performance Check | Browser DevTools | Feed load time, API response times, memory leaks on long sessions | Developer |
| Unique Feature Testing | Manual + Scripts | Fingerprint duplicate detection with real files, Shield Mode simulation with rapid comment script | Developer |

## 7.2 Unit Test Cases

| Test ID | Function Tested | Input | Expected Output | Status |
| --- | --- | --- | --- | --- |
| UT-01 | generateFingerprint(text, mediaHash) | 'hello world', 'abc123' | 64-character hex string | ⬜ |
| UT-02 | generateFingerprint(text, mediaHash) | Same inputs as UT-01 | Identical hex string (deterministic) | ⬜ |
| UT-03 | generateFingerprint(text, mediaHash) | Different text, same media | Different hex string | ⬜ |
| UT-04 | languageFilter.score(text) | 'I hate you so much!!' | Score >= 7 (rejected) | ⬜ |
| UT-05 | languageFilter.score(text) | 'Great post, loved it!' | Score < 4 (approved) | ⬜ |
| UT-06 | tokenService.verifyAccessToken(token) | Expired JWT | Throws TokenExpiredError | ⬜ |
| UT-07 | tokenService.verifyAccessToken(token) | Tampered JWT | Throws JsonWebTokenError | ⬜ |
| UT-08 | shieldService.checkVelocity(postId) | Post with 20 new non-follower comments | Returns { shouldActivate: true } | ⬜ |
| UT-09 | shieldService.checkVelocity(postId) | Post with 3 new non-follower comments | Returns { shouldActivate: false } | ⬜ |

## 7.3 API Integration Test Cases

| Test ID | Endpoint | Scenario | Expected HTTP Status | Status |
| --- | --- | --- | --- | --- |
| IT-01 | POST /auth/register | Valid new user data | 201 | ⬜ |
| IT-02 | POST /auth/register | Duplicate email | 409 | ⬜ |
| IT-03 | POST /auth/login | Wrong password | 401 | ⬜ |
| IT-04 | POST /auth/login | Unverified email | 403 | ⬜ |
| IT-05 | POST /posts | Valid post without auth token | 401 | ⬜ |
| IT-06 | POST /posts | Valid post with auth, image attached | 201 + fingerprint in DB | ⬜ |
| IT-07 | POST /posts | Re-upload of exact same image | 201 + is_reshare=1 | ⬜ |
| IT-08 | DELETE /posts/:id | User deletes another user's post | 403 | ⬜ |
| IT-09 | POST /posts/:id/comments | Toxic comment text | 201 + status='rejected' | ⬜ |
| IT-10 | POST /posts/:id/shield/activate | Non-owner tries to activate shield | 403 | ⬜ |
| IT-11 | GET /posts/feed | User with no follows | 200 + empty array | ⬜ |
| IT-12 | POST /users/:id/follow | User tries to follow themselves | 422 | ⬜ |
| IT-13 | PUT /notifications/read-all | Valid request | 200 + all marked read | ⬜ |

## 7.4 Unique Feature Test Cases

### Fingerprinting Tests

| Scenario | Steps | Expected Result |
| --- | --- | --- |
| Exact duplicate image | 1. Post image A as User 1. 2. Post same image A as User 2. | User 2's post shows 'Originally by User 1' badge. User 1 gets notification. |
| Near-identical text | 1. Post text 'Hello world!' as User 1. 2. Post 'hello world!' (lowercase) as User 2. | Detected as duplicate (normalization handles case difference) |
| Slightly edited text | 1. Post text 'Original post content' as User 1. 2. Post 'Original post content.' (added period) as User 2. | NOT detected (hash is different — by design) |
| Different image, same text | 1. Post text + Image A. 2. Post same text + Image B. | NOT detected (media hash differs) |

### Shield Mode Tests

| Scenario | Steps | Expected Result |
| --- | --- | --- |
| Auto-activation | 1. Create post as User A. 2. Run script: 20 non-follower users comment in 2 minutes. 3. Wait 60 seconds for cron. | Shield activates. User A gets socket notification. New non-follower comments queued. |
| Follower bypass | 1. Shield active on post. 2. Comment as a follower of post owner. | Comment goes live immediately (not queued). Followers are never blocked. |
| Auto-deactivation | 1. Shield active. 2. No new comments for 10 minutes. | Shield deactivates automatically. Pending comments released. |
| Manual activation | 1. Call POST /posts/:id/shield/activate as post owner. | Shield immediately active on that post. |

## 7.5 Bug Tracking

| Bug ID | Description | Severity | Status | Fix |
| --- | --- | --- | --- | --- |
| BUG-001 | [Template] Fingerprint not generated for text-only posts (no media) | High | ⬜ Open |  |
| BUG-002 | [Template] Shield cron crashes silently if DB connection drops | High | ⬜ Open |  |
| BUG-003 | [Template] Like count not updating in real-time on feed | Medium | ⬜ Open |  |
| BUG-004 | [Template] Profile avatar not displaying after upload | Low | ⬜ Open |  |

📌 Bug tracker to be filled during Sprint 6 testing. Each found bug gets an ID, severity rating, and documented fix before submission.

# Phase 6 — Deployment

## Duration: Days 50–56  |  Sprint 7

Deployment is the phase where the working application is made accessible to real users (or evaluators). For a college project, this means hosting the frontend, backend, and database on free-tier cloud services and ensuring the application runs without the development machine being on.

## 8.1 Deployment Architecture

| Component | Platform | Why | Cost |
| --- | --- | --- | --- |
| React Frontend | Vercel or Netlify | Free tier, automatic deploys from GitHub, global CDN, zero config for React apps | Free |
| Node.js Backend | Render or Railway | Free tier Node.js hosting, supports environment variables, auto-restart on crash | Free |
| MySQL Database | PlanetScale or Railway | Free tier MySQL-compatible cloud database, automatic backups | Free |
| File Storage | Local disk (dev) / Cloudinary (prod) | Cloudinary free tier: 25GB storage, CDN delivery, direct URL storage | Free |
| Email (SMTP) | Gmail SMTP via Nodemailer | Free with Gmail account; no external service needed for college scope | Free |

## 8.2 Deployment Checklist

| Item | Status |
| --- | --- |
| All .env variables set in production environment (NOT .env file pushed to Git) | ⬜ |
| NODE_ENV=production set (disables verbose error messages) | ⬜ |
| MySQL schema migrations run on production database | ⬜ |
| CORS origin updated to production frontend URL | ⬜ |
| Socket.io CORS updated to production frontend URL | ⬜ |
| JWT_SECRET is a long random string (not 'secret' or 'test') | ⬜ |
| bcrypt cost factor confirmed as 12 | ⬜ |
| File upload paths correct for production filesystem | ⬜ |
| node-cron Shield job confirmed running in production | ⬜ |
| Test full user flow on production URL before submission | ⬜ |
| README.md updated with live URL and setup instructions | ⬜ |
| .gitignore includes: .env, node_modules/, /uploads | ⬜ |

## 8.3 Environment Variables Reference

| Variable | Description | Example Value |
| --- | --- | --- |
| PORT | Server port | 5000 |
| DB_HOST | MySQL host | cloud-db-host.planetscale.com |
| DB_USER | MySQL username | truevoice_user |
| DB_PASSWORD | MySQL password | ***** (never hardcode) |
| DB_NAME | MySQL database name | truevoice_db |
| JWT_SECRET | Secret for signing access tokens | 64-char random string |
| JWT_REFRESH_SECRET | Secret for signing refresh tokens | Different 64-char random string |
| JWT_EXPIRY | Access token expiry | 15m |
| JWT_REFRESH_EXPIRY | Refresh token expiry | 7d |
| EMAIL_HOST | SMTP host | smtp.gmail.com |
| EMAIL_USER | SMTP email address | yourapp@gmail.com |
| EMAIL_PASS | SMTP app password | ***** (never hardcode) |
| CLIENT_URL | Frontend URL for CORS + email links | https://truevoice.vercel.app |
| NODE_ENV | Environment mode | production |

## 8.4 Phase 6 Deliverables

| Deliverable | Status |
| --- | --- |
| Application live on public URL | ⬜ |
| All SDLC documents complete | ⬜ |
| System Design Document (SDD) | ✅ Complete |
| SDLC Document (this document) | ✅ Complete |
| Project Proposal | ✅ Complete |
| Project Synopsis | ✅ Complete |
| Project Report | ✅ Complete |
| README.md with setup instructions + live URL | ⬜ |
| Postman collection exported and documented | ⬜ |
| Final presentation / viva preparation | ⬜ |

# Phase 7 — Maintenance (Post-Submission)

## Ongoing after submission

Maintenance is the longest phase of any software product's life. For TrueVoice, the maintenance phase covers bug fixes found after submission and the roadmap for future features.

## 9.1 Types of Maintenance

| Maintenance Type | Description | TrueVoice Examples |
| --- | --- | --- |
| Corrective Maintenance | Fix bugs found after deployment | Fix edge cases in fingerprint normalization, shield threshold tuning |
| Adaptive Maintenance | Adapt to environmental changes | Update Node.js version, MySQL version, React version, fix breaking API changes |
| Perfective Maintenance | Improve performance and add features | Add Redis caching for feed, add perceptual hashing (pHash), add search |
| Preventive Maintenance | Refactor to prevent future bugs | Add more unit tests, improve error logging, code cleanup |

## 9.2 Post-Submission Roadmap

| Priority | Feature | Complexity | Value |
| --- | --- | --- | --- |
| P1 — High | Perceptual hashing (pHash) for near-duplicate image detection | High | Greatly improves OriginPost accuracy |
| P1 — High | Adaptive Shield thresholds based on per-user comment history | High | Reduces false Shield activations on popular posts |
| P2 — Medium | Full-text post and user search | Medium | Essential for discoverability at scale |
| P2 — Medium | Redis caching for news feed | Medium | Dramatically reduces DB load for active users |
| P2 — Medium | ML toxicity scoring (Google Perspective API) | Medium | More accurate than keyword blocklist |
| P3 — Low | Direct messaging between users | High | Expected social media feature |
| P3 — Low | Stories (24-hour ephemeral posts) | Medium | Engagement feature |
| P3 — Low | React Native mobile app | High | Extends platform to mobile users |

# 10. SDLC Summary

## 10.1 Complete Phase Timeline

| Phase | Name | Duration | Start | End | Key Output |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | Planning | 4 days | Day 1 | Day 4 | Project plan, risk register, tech decisions |
| Phase 2 | Requirements Analysis | 5 days | Day 3 | Day 7 | Full requirements doc, use cases |
| Phase 3 | System Design | 7 days | Day 8 | Day 14 | SDD, DB schema, API contracts |
| Phase 4 | Implementation | 28 days | Day 15 | Day 42 | Working full-stack application |
| Phase 5 | Testing & QA | 7 days | Day 43 | Day 49 | Test results, bug fix log |
| Phase 6 | Deployment | 7 days | Day 50 | Day 56 | Live app + all documents |
| Phase 7 | Maintenance | Ongoing | Day 57 | — | Bug fixes, new features |

## 10.2 Document Inventory

| Document | Purpose | Status |
| --- | --- | --- |
| Project Proposal | Introduces the project idea, objectives, scope, and timeline to evaluators | ✅ Complete |
| Project Synopsis | Concise 2-3 page summary of the entire project — the elevator pitch version | ✅ Complete |
| Project Report | Full academic report covering all development phases and outcomes | ✅ Complete |
| System Design Document | Technical blueprint: architecture, DB schema, APIs, feature design algorithms | ✅ Complete |
| SDLC Document | Process framework: all 6 phases, tasks, timelines, test cases, risks | ✅ Complete |
| README.md | Developer guide: setup instructions, environment variables, run commands | ⬜ Pending |
| Postman Collection | Exported collection of all API tests for evaluator review | ⬜ Pending |

## 10.3 Success Criteria

The TrueVoice project is considered successfully complete when all of the following are true:

- All Must Have requirements (FR-01 through FR-33) are implemented and tested

- All unit tests pass (UT-01 through UT-09)

- All integration tests pass (IT-01 through IT-13)

- Fingerprint duplicate detection correctly identifies and credits re-uploaded content

- Shield Mode correctly activates on simulated pile-on (20 non-follower comments in 2 minutes)

- Real-time notifications arrive without page refresh

- Application is live on a public URL and accessible without running local server

- All 5 documents (Proposal, Synopsis, Report, SDD, SDLC) are complete and submitted

— End of SDLC Document —

TrueVoice SDLC v1.0  |  Agile Model  |  8 Weeks